## Shop Application Roadmap - Time
Source
Shop Application Roadmap
Item (REQUIRED) | Start Date | End Date | Owner (Technology Roadmap) | Status (Technology Roadmap) | Theme (Technology Roadmap) | Department
SignIn / Sign Up | 2020-04-02 | 2020-04-10 | Omar (Middle level) | In Progress | Android / IOS team | Development
Orders History | 2020-04-29 | 2020-05-09 | Omar (Middle level) | Testing | Android / IOS team | Development
IOS Application Design | 2020-03-01 | 2020-03-30 | Farah | Completed | Design Team | DesignDepartment
API Documentation | 2020-03-15 | 2020-03-31 | Milestones | Completed | Backend | Development
Sign Up with Google |  |  |  | In Progress | Android / IOS team | Development
Sign Up with Sociala |  |  |  | Backlog | Android / IOS team | Development
Setup Payment | 2020-04-16 | 2020-04-24 | Omar (Middle level) | In Progress | Android / IOS team | Development
Creating Products Feed | 2020-04-01 | 2020-04-21 | Jamie (Senior Level) | Completed | Android / IOS team | Development
Section Deal of the Day |  |  |  |  | Android / IOS team
Section Recommended for user |  |  |  |  | Android / IOS team
Popula Deals |  |  |  |  | Android / IOS team
Deals by categories |  |  |  |  | Android / IOS team
Search | 2020-05-21 | 2020-05-31 | Jamie (Senior Level) | Backlog | Android / IOS team | Development
Setup Account | 2020-04-07 | 2020-04-26 | Carly (Middle Level) | Backlog | Android / IOS team | Development
Orders Section |  |  |  | Backlog | Android / IOS team
Account Settings |  |  |  | Backlog | Android / IOS team
Wallet |  |  |  | Backlog | Android / IOS team
Messages and Notificaions |  |  |  | Backlog | Android / IOS team
Track order | 2020-05-02 | 2020-05-17 | Jamie (Senior Level) | Completed | Android / IOS team | Development
Push Notifications | 2020-05-12 | 2020-05-18 | Carly (Middle Level) | In Progress | Android / IOS team | Development
Filter | 2020-05-19 | 2020-05-28 | Omar (Middle level) | Backlog | Android / IOS team | Development
Options for Cart's item | 2020-04-29 | 2020-05-09 | Carly (Middle Level) | In Progress | Android / IOS team | Development
Delete Item From Cart |  |  |  |  | Android / IOS team
Save for Later |  |  |  |  | Android / IOS team
Compare with Similar Items |  |  |  |  | Android / IOS team
Creating product Details Page | 2020-04-01 | 2020-05-30 | Maria (Senior) | Completed | Android / IOS team | Development
Add product to Cart | 2020-04-05 | 2020-04-08 | Maria (Senior) | Backlog | Android / IOS team
Quick order | 2020-04-08 | 2020-04-14 | Maria (Senior) | Backlog | Android / IOS team
Share Item | 2020-05-22 | 2020-05-30 | Maria (Senior) | Backlog | Android / IOS team | Development
Sponsored products related to selected Item | 2020-05-17 | 2020-05-30 | Maria (Senior) | Backlog | Android / IOS team | Development
Customer reviews | 2020-04-01 | 2020-04-15 | Maria (Senior) | Backlog | Android / IOS team | Development
Android Application Design | 2020-03-01 | 2020-03-30 | Jone | Completed | Design Team | DesignDepartment
Creating Shop app APIs | 2020-03-01 | 2020-03-25 | Alex | Completed | Backend | Development
Buy Again | 2020-06-01 | 2020-06-15 | Carly (Middle Level) | In Progress | Android / IOS team | Development
Shop by Department | 2020-06-10 | 2020-06-15 | Omar (Middle level) | In Progress | Android / IOS team | Development
Prime membership | 2020-06-10 | 2020-06-20 | Jamie (Senior Level) | In Progress | Android / IOS team | Development
Membership and subscriptions | 2020-06-16 | 2020-06-23 | Maria (Senior) | In Progress | Android / IOS team | Development
Personalized Content | 2020-06-17 | 2020-06-24 | Carly (Middle Level) | In Progress | Android / IOS team | Development
Voice search | 2020-06-17 | 2020-06-23 | Omar (Middle level) | In Progress | Android / IOS team | Development
Search by image | 2020-06-07 | 2020-06-13 | Maria (Senior) | In Progress | Android / IOS team | Development
General bug fixing | 2020-04-23 | 2020-04-30 | Jamie (Senior Level) | In Progress | Android / IOS team | Development
Bug fixing and improvements | 2020-05-20 | 2020-05-30 | Carly (Middle Level) | In Progress | Android / IOS team | Development